## R1 AI-first estimate
ICE Services Project Lifecycle Platform
AI-first R1 project estimate using BMAD, Spec Kit and Ralph
Metric | Low | Working | High |  |  | Implementation metric | Low | Working | High
Human delivery effort (hours) | 561 | 788 | 1052 |  |  | Direct Ralph oversight (human hours) | 70 | 85 | 110
Equivalent person-months | 3.5063 | 4.925 | 6.575 |  |  | External-system validation (human hours) | 75 | 99 | 150
Planning calendar (weeks) | 8 | 10 | 12 |  |  | Ralph runtime (machine hours) | 200 | 300 | 400
R1 human effort by category |  | Low | Working | High
Category | Included work | Hours | Hours | Hours
BMAD product and requirements package | Source synthesis, PRD, roles, scope, traceability and release framing | 16 | 24 | 32
UX workflow and screen specification | Journeys, states, screen inventory and acceptance flows | 20 | 30 | 40
Architecture and decision review | Application, identity, documents, persistence and integration patterns | 30 | 45 | 60
API spikes and technical validation | T-Sheets, Procurement, HR, AR and document repository validation | 40 | 60 | 80
Spec Kit feature preparation | Specification, clarify, plan, tasks and readiness review for R1 features | 40 | 50 | 60
Direct Ralph oversight | Feature setup, exceptions, review, acceptance and checkpoints | 70 | 85 | 110
External integration validation | Real-system credentials, mappings, API behavior and troubleshooting | 75 | 99 | 150
System-wide automated test review | Cross-feature integration, regression and performance validation | 60 | 90 | 120
UAT preparation and support | Scenarios, user support, defect triage and accepted corrections | 60 | 90 | 120
Migration validation and cutover | Legacy profiling, mapping, rehearsal, reconciliation and production load | 60 | 90 | 120
Training and production support | Guides, training, release support and initial hypercare | 30 | 45 | 60
Project coordination | Planning, decisions, status, demonstrations and release coordination | 60 | 80 | 100
TOTAL HUMAN EFFORT |  | 561 | 788 | 1052
R1 implementation detail
ID | Capability | Source requirements | Setup | Ralph exceptions | Review and acceptance | Merge / checkpoint | External-system work | Direct Ralph oversight | Total human hours | Notes | Agent runtime low | Agent runtime high
S01 | Platform foundation and CI/CD | PP-045, PP-056, PP-057 | 0.5 | 1 | 2 | 1 | 3.5 | 4.5 | 8 | Ralph performs implementation and developer tests | 8 | 16
S02 | Identity and access | PP-041, PP-049–052, PP-070 | 0.5 | 1.5 | 3 | 1 | 6 | 6 | 12 | Ralph performs implementation and developer tests | 10 | 20
S03 | Master data and configuration | PP-033–037, PP-053 | 0.5 | 0.5 | 2 | 1 | 2 | 4 | 6 | Ralph performs implementation and developer tests | 4 | 8
S04 | SOW core setup | PP-001–005, PP-009 | 0.5 | 1 | 2.5 | 1 | 3 | 5 | 8 | Ralph performs implementation and developer tests | 8 | 16
S05 | Document management | PP-006, PP-046 | 0.5 | 1 | 2.5 | 1 | 5 | 5 | 10 | Ralph performs implementation and developer tests | 8 | 18
S06 | SOW lifecycle and audit | PP-007–008, PP-017, PP-022, PP-042 | 0.5 | 1 | 3 | 1 | 4.5 | 5.5 | 10 | Ralph performs implementation and developer tests | 10 | 20
S07 | T-Sheets provisioning | PP-010–013, PP-016, PP-039, PP-047 | 0.5 | 2 | 3.5 | 1 | 13 | 7 | 20 | Higher real-system and data uncertainty | 20 | 40
S08 | Labor retrieval and basic OT | PP-014, R1 portion of PP-015 | 0.5 | 1.5 | 3 | 1 | 10 | 6 | 16 | Ralph performs implementation and developer tests | 16 | 32
S09 | Procurement and project costs | PP-024, PP-038 | 0.5 | 2 | 3.5 | 1 | 13 | 7 | 20 | Higher real-system and data uncertainty | 20 | 40
S10 | Project financial tracking | PP-018–019 | 0.5 | 1 | 2.5 | 1 | 3 | 5 | 8 | Ralph performs implementation and developer tests | 8 | 16
S11 | Billing packet assembly | PP-023–024, PP-028 | 0.5 | 1.5 | 3.5 | 1 | 7.5 | 6.5 | 14 | Ralph performs implementation and developer tests | 16 | 32
S12 | Closeout and reconciliation | PP-026, PP-030, PP-068–069 | 0.5 | 1.5 | 4 | 1 | 7 | 7 | 14 | Ralph performs implementation and developer tests | 18 | 36
S13 | AR handoff and billing tracking | PP-029, PP-031, PP-040 | 0.5 | 1 | 2.5 | 1 | 5 | 5 | 10 | Ralph performs implementation and developer tests | 10 | 20
S15 | Data migration and cutover | PP-044 | 0.5 | 2 | 3.5 | 1 | 13 | 7 | 20 | Higher real-system and data uncertainty | 15 | 30
X01 | Release and production readiness | Cross-cutting R1 release work | 0.5 | 1 | 2 | 1 | 3.5 | 4.5 | 8 | Ralph performs implementation and developer tests | 8 | 16
AGT | Cross-feature agent regression and refactoring | Agent-only runtime allowance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Unattended cross-feature agent work; no human labor added | 21 | 40
TOTAL |  |  | 7.5 | 19.5 | 43 | 15 | 99 | 85 | 184 |  | 200 | 400
Estimate assumptions
Human hours exclude unattended Ralph runtime. Machine runtime is tracked separately and does not convert directly into labor hours.
Ralph is assumed to implement, test, correct, document and checkpoint each implementation-ready feature with limited intervention.
The working estimate is 788 human hours. The range reflects API behavior, source-data quality, client decision speed and UAT findings.
The calendar plan assumes overlapping workstreams. A single local Qwen endpoint serializes heavy Ralph runs; multiple endpoints shorten elapsed time.
R1 includes basic overtime behavior needed for billing. Advanced configurable overtime, progress billing, equipment integration and accrual reporting remain later releases.
Estimating, CRM/opportunity management, Procore, full GL posting, full progress-billing workflow, licenses and ongoing support are excluded.
Client employee time spent performing UAT is excluded. Delivery-team UAT preparation, support and accepted corrections are included.
All yellow estimate cells are editable. Formula totals update automatically.