## R1 AI-first estimate
ICE Services Project Lifecycle Platform
AI-first R1 project estimate using BMAD, Spec Kit and Claude Code
Metric | Low | High
Human delivery effort (hours) | 502 | 556
Equivalent person-months | 3.1375 | 3.475
Planning calendar (weeks) | 10 | 13
R1 effort by category |  | Low | High
Category | Included work | Hours | Hours
BMAD product and requirements package | Source synthesis, PRD, roles, scope, traceability and release framing | 14 | 20
UX workflow and screen specification | Journeys, states, screen inventory and acceptance flows | 16 | 20
Architecture and decision review | Application, identity, documents, persistence and integration patterns | 24 | 30
API spikes and technical validation | T-Sheets, Procurement, HR, AR and document repository validation | 40 | 40
Spec Kit feature preparation | Specification, clarify, plan, tasks and readiness review for R1 features | 24 | 32
Claude Code oversight | Feature setup, exceptions, review, acceptance and checkpoints | 85 | 85
External integration validation | Real-system credentials, mappings, API behavior and troubleshooting | 99 | 99
System-wide automated test review | Cross-feature integration, regression and performance validation | 40 | 50
UAT preparation and support | Scenarios, user support, defect triage and accepted corrections | 50 | 50
Migration validation and cutover | Legacy profiling, mapping, rehearsal, reconciliation and production load | 40 | 50
Training and production support | Guides, training, release support and initial hypercare | 30 | 30
Project coordination | Planning, decisions, status, demonstrations and release coordination | 40 | 50
TOTAL HUMAN EFFORT |  | 502 | 556
R1 implementation detail
ID | Capability | Source requirements | Setup | Exceptions | Review and acceptance | Merge / checkpoint | External-system work | Human oversight | Total human hours | Agent runtime low | Agent runtime high
S01 | Platform foundation and CI/CD | PP-045, PP-056, PP-057 | 0.5 | 1 | 2 | 1 | 3.5 | 4.5 | 8 | 8 | 16
S02 | Identity and access | PP-041, PP-049–052, PP-070 | 0.5 | 1.5 | 3 | 1 | 6 | 6 | 12 | 10 | 20
S03 | Master data and configuration | PP-033–037, PP-053 | 0.5 | 0.5 | 2 | 1 | 2 | 4 | 6 | 4 | 8
S04 | SOW core setup | PP-001–005, PP-009 | 0.5 | 1 | 2.5 | 1 | 3 | 5 | 8 | 8 | 16
S05 | Document management | PP-006, PP-046 | 0.5 | 1 | 2.5 | 1 | 5 | 5 | 10 | 8 | 18
S06 | SOW lifecycle and audit | PP-007–008, PP-017, PP-022, PP-042 | 0.5 | 1 | 3 | 1 | 4.5 | 5.5 | 10 | 10 | 20
S07 | T-Sheets provisioning | PP-010–013, PP-016, PP-039, PP-047 | 0.5 | 2 | 3.5 | 1 | 13 | 7 | 20 | 20 | 40
S08 | Labor retrieval and basic OT | PP-014, R1 portion of PP-015 | 0.5 | 1.5 | 3 | 1 | 10 | 6 | 16 | 16 | 32
S09 | Procurement and project costs | PP-024, PP-038 | 0.5 | 2 | 3.5 | 1 | 13 | 7 | 20 | 20 | 40
S10 | Project financial tracking | PP-018–019 | 0.5 | 1 | 2.5 | 1 | 3 | 5 | 8 | 8 | 16
S11 | Billing packet assembly | PP-023–024, PP-028 | 0.5 | 1.5 | 3.5 | 1 | 7.5 | 6.5 | 14 | 16 | 32
S12 | Closeout and reconciliation | PP-026, PP-030, PP-068–069 | 0.5 | 1.5 | 4 | 1 | 7 | 7 | 14 | 18 | 36
S13 | AR handoff and billing tracking | PP-029, PP-031, PP-040 | 0.5 | 1 | 2.5 | 1 | 5 | 5 | 10 | 10 | 20
S15 | Data migration and cutover | PP-044 | 0.5 | 2 | 3.5 | 1 | 13 | 7 | 20 | 15 | 30
X01 | Release and production readiness | Cross-cutting R1 release work | 0.5 | 1 | 2 | 1 | 3.5 | 4.5 | 8 | 8 | 16
AGT | Cross-feature agent regression and refactoring | Agent-only runtime allowance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 40
TOTAL |  |  | 7.5 | 19.5 | 43 | 15 | 99 | 85 | 184 | 200 | 400
Estimate assumptions
Human hours exclude unattended Claude Code runtime. Machine runtime is tracked separately and does not convert directly into labor hours.
Claude Code is assumed to implement, test, correct, document and checkpoint each implementation-ready feature with limited intervention.
The working estimate is 492 human hours. The range reflects API behavior, source-data quality, client decision speed and UAT findings.
The calendar plan assumes overlapping workstreams.
R1 includes basic overtime behavior needed for billing. Advanced configurable overtime, progress billing, equipment integration and accrual reporting remain later releases.
Client employee time spent performing UAT is excluded. Delivery-team UAT preparation, support and accepted corrections are included.
All yellow estimate cells are editable. Formula totals update automatically.